Completed Activities

| Activity | Objectives | Who Involved | Date Completed | Outcome/Issues/Concerns |
| --- | --- | --- | --- | --- |
| Set Up Steering Group | Agree members with Cluster of Roseland Parishes | Julian German (Cornwall Councillor) and Parish Councils. Jon Smith Elected as Chair, Colin Hastings as Vice Chair | June 2013 | 15 members of very varied backgrounds |
| Establish Terms of Reference | Agreed by Parishes and Steering Group | JG, JS, Steering Group, Parish Councils | June 2013 | Accepted by all parties |
| Develop Project Plan | Agreed by Steering Group | JS, Steering Group | June 2013, August 2013 | Original Plan accepted in June. More detailed version accepted in August |
| Apply for Finance | Application made to Department for Communities and Local Government | JS | July 2013 | Grant of £7000 awarded. Arrangements made with St Mawes and St Just Society to handle banking for the NDP |
| Apply for Direct Support | Application made through Locality | JS | July 2013 | Awarded 10-24 days of Consultancy (through Planning Aid England) |
| Questionnaire 1 | Simple Questionnaire using heading flagged at preliminary Public Meetings | JG, volunteers from Parish Councils. | Dec 2012 to Feb 2013 | Minimal publicity 397 responses Analysis ranked the importance of the flagged issues |
| Article in August Roseland Magazine and on Roseland Online | Short informative article re: where we are | JS, John Adams (Steering Group Secretary) | July 2013 | Slight typo error in printed version |
| Set up Website and email address | www.roselandplan.org info@roselandplan.org | JA, Hayley Emery, CH | July 2013 August 2013 | Simple version online in July. Updated version online in August. |
| Article in September Roseland Mag & R-O. | Short informative article re: where we are | JS, JA | August 2013 | Typo error corrected |
| Article in October Roseland Mag & R-O. | Short informative article re: where we are | JA | September 2013 |  |
| NDP Stand at Summer Events | Gazebo-based stand, maps, posters, questionnaires etc to stimulate interest & generate more data. | CH plus a set of 11 volunteers, mostly from the Steering Group | July and August 2013 | Visibility of the NDP high. In-depth conversations re: aims and process. About 30 questionnaires completed per venue = 175 in total. |
| Analysis of Hopes and Fears for the Future of the Roseland | Stimulate discussion at Summer Events. Gather list of important topics for Autumn Community Engagement and for Questionnaire 2. | CH | August 2013 | List of important hopes/fears for the future identified = ZZ respondents. |
| First Letter & Communication Questionnaire | Letter/Questionnaire delivered to each elector on the Roseland | Parish Distribution Teams headed by: David Hubbard (St Just), Ralph German (Gerrans), David Giles (Ruan), Derek Julyan (Philleigh), Jon Smith (Veryan) | Distribution mostly completed in August 2013. | Distribution not totally perfect. Not quite finished by end August. Responses arriving over many weeks. |
| Analysis of Communication Questionnaires from First Letter and Summer Events | Information about how best to reach the Community | Sue Wagstaff ( + bit JA) | Completed by mid September 2013 | Progressed well. Overall list and individual Parish Lists. |
| Construction of Email contact list | From Communication Questionnaire and from forms from Summer Events | Sue Wagstaff (+ bit JA) | Completed by mid September 2013 | Progressed well. 347 unique email addresses = 387 contacts. |
| Gathering background information of likely relevance to important Planning topics | From Cornwall Council, AONB, Locality etc | JS, Graham Webb, David Hubbard, Geoff Pring | By August 2013. | Satisfactory ‘evidence base’ gathered by mid September 2013. Will need reviewing periodically for gaps. |
| In-depth (re)analysis of qualitative data (written comments) from Q1 & Summer Events | To generate firm basis for Questionnaire 2. | Sue Wagstaff, JS | Completed well before end September 2013. |  |
| Update website (minutes, updated diagrams, more links) | Continual improvement and maintain interest | JA, Hayley Emery. | By end September 2013/ early October. | Done. |
| Write/Print/Distribute Letter/ Email2 | Keep up communication about what the NDP is, and launch ‘Have Your Say’ campaign. | Text – JS/CW Design – JA Printing – JA Distribution – Parish Teams | Distribution in October. | Distributed by Email to Parish Lists and also by hand. |
| Article in November Roseland Mag & R-O. |  |  | By 10 October 2013 | Article done for RM. Sent to R-O in early November. |
| Design and Print Questionnaire 2 | Produce Drafts for SG and improve (2 or 3 stages?); ‘Beta test’ with SG and selected others; formal approval by SG, JG, EB etc; print. | JS, CH, JA, Angela Warwick | Completion & printing by end Oct. | Done by Friday November 1st. |
| Email/Facebook actions listed in MT minutes of 4th September 2013 etc | Thank people for providing emails. Answer queries/questions. Request for more and FB friends through their contacts. | JA construct Parish-based group lists. CH construct email+FB list. Hayley Emery to post new material on FB. JA construct group emailing list and send out relevant email. | Parish-based Email lists developed and Emails sent by end Sept / early October. | Done in October. |
| Article for December Roseland Mag & R-O. | Maintain and improve communication. Include info about public Q2 meetings in December. | JA/CH/JS | By 10 November 2013. | Done. |

Background Activities in Progress

| Activity | Objectives | Who Involved | Date for Completion or Review | Outcome/Issues/Concerns |
| --- | --- | --- | --- | --- |
| Housing Needs Information | Assessment of Housing Needs through info from Cornwall Council & Homechoice Register. | Trudi van der Wolde, JS | By end September 2013/ early October. | Trudi’s conclusion is that 55 dwellings are required across the Roseland. More detail re: location etc will be presented in the SG Meeting in December. |
| Gathering background environmental / wildlife information of likely relevance to the Plan | Determine impact / constraints on our Plan set by regulations relating to ‘natural’ matters | DHa and SG members | Summary ready for Dec SG meeting. | DHa and the Cornwall Wildlife Trust Rep will present at the December SG Meeting. |
| Mapping Exercise - Locate Stakeholders, activities, businesses, buildings on Parish Maps | To identify stakeholders, businesses, buildings, land of potential relevance to the Plan | GW and relevant SG members (DG, RG, BW, RW). JS to obtain full colour maps. | Originally planned for end September 2013. Needed for Autumn events. | GW and Parish reps will be invited to a MT meeting to finalise what goes on the maps (to be obtained by JS from Parishes or Cornwall Council – may require small payment). |

Q2-Related Activities in Progress

| Activity | Objectives | Who Involved | Date for Completion or Review | Outcome/Issues/Concerns |
| --- | --- | --- | --- | --- |
| Update website (minutes, updated text, more links, more on Q2) | Continual improvement and maintain interest | JA, Hayley Emery. | By 6 Nov 2013. | Partially done. Should be complete by 20 Nov 2013. |
| Roseland Online – Put up Nov Roseland Mag article and other material, including some about Q2. | Maintain and improve communication. | Sue Wagstaff | By 10th November 2013. | Initial material put up. |
| Organise Public Drop in Meetings during Q2 period | Explain Q2; help some complete the forms | CH to coordinate with help from Parish Reps. SG members (and others) to be involved in events. | Dates of events needed before Roseland Mag deadline. | Done by early November. Dates publicised by email and on Facebook and will be on posters soon (see below). |
| Write/Print/Distribute Posters | More on ‘Have Your Say’ Campaign | Design – JA Printing – JS Lamination - CH Distribution – Parish Teams | Design/print/laminate as required in November and December. | Posters for each Parish will be available from 20 Nov 2013. |
| Write report describing process of finalising Q2 | To provide paper trail to show the objectivity of the process | JA | By end November 2013. |  |
| Data entry from returned Questionnaires. Includes auditing by ‘external’ person. | Basis of Plan | Terry Hedge - system design, merging of data sets and production of answers to ‘queries’. Sue Wagstaff PLUS 2 or 3 (?) helpers – Data Entry. ??????? – Auditing. | From mid-November 2013 to early January 2014. | System designed by Terry Hedge seems OK. May or may not be a problem of manpower for data entry. Need to arrange auditor. |
| Formal Report on outcome of Q2 | Appendix of Plan (probably). | MT | By mid- January (probably). |  |

Non-Q2 Activities in Progress or Planned for the Near Future

| Activity | Objectives | Who Involved | Date for Completion or Review | Outcome/Issues/Concerns |
| --- | --- | --- | --- | --- |
| Write Consultation Statement | Requirement of NDP | CH | Draft originally planned for end Sept. Rescheduled for November. | On track. |
| Mailshot to Stakeholders using list from Mapping Exercise plus CH Stakeholder Engagement List | Explanation of what we are doing and seeking input | JS, CH + Parish reps Advice from Consultants. | In November 2013. | List of stakeholders being constructed from mapping exercise and CH stakeholder document. |
| Update website (minutes, updated diagrams, photos of SG members, more links) | Continual improvement and maintain interest | JA, Hayley Emery. | By end November 2013. |  |
| Produce updated Project Plan and Activity List for early 2014. | Avoid loss of momentum. | MT | Before December Steering Group Meeting. |  |

# Text boxes

Update of 17.11.2013