Minutes of Closed Meeting of Roseland Neighbourhood Development Plan (NDP) Management Team

at Little Treviles 3.00pm on 21st November 2014

Present: Jon Smith, John Adams and Sue Wagstaff

Apologies received from Colin Hastings

- Minutes

The minutes of the meetings held on 27th October 2014 and 7th November 2014 were approved and signed by the Chairman

- Matters arising – none

- Consultation Statement

CH had circulated the latest version of his document but JA has subsequently carried out some changes. The document is based on Much Wenlock’s Statement of Public Consultation, although theirs is shorter. The present version was reviewed page by page and agreed changes noted by JA. He envisages 2 days of work to update but will have ready for Monday 24th November 2014.

- Documents for Submission

The status of all required documentation was then reviewed:

Plan effectively done

Basic Conditions Statement – Graham Webb (GW) has only a few changes to make, so JA agreed to ask GW to pass document to JA in next few days so can be passed on to Rob Lacey (RL) for final review.

Consultation Statement – nearly done (see above)

Proposal Maps – waiting on Rob Lacey to produce/provide

Area Profile – GW has a few amendments to make – JA to chase up – and then awaiting settlement boundary maps from Cornwall Council to complete

LLCA – Caroline Coldwell has sent the latest version to JS who has asked that any opinions be removed from the text but confirmed that the document is much improved. However as the final version had been requested for today, JS will chase.

JS expressed concern that the preferred submission date of 8th December 2014 was fast approaching and JA pointed out that they should have the week before submission to carry out final checks of all documents.

JS will chase Rob Wing for a letter dated 8th December 2014 to accompany documents, and will also check with RL whether all documents need to be submitted in hard copy.

- AOB

A discussion ensued about the implementation of the Plan – how much assistance/guidance would be needed by Parish Councils and how this would be provided; future projects – how to encourage the best qualified people to become involved; the Steering Group – whether some members might want to stand down and whether (hopefully) others want to join, especially considering skills needed for implementation and future projects.

Meeting closed at 4.55pm				S Wagstaff

Action points:

JS –

- Chase up LLCA document

- Chase Rob Wing for submission letter

- Check with RL re: hard copy documents for submission

JA –

- Update Consultation Statement with agreed changes for Monday 24th November 2014

- Chase GW for Basic Conditions Statement and Area Profile