Minutes of Closed Meeting of Roseland Neighbourhood Development Plan (NDP) Management Team

at Little Treviles 10.30am on 23rd March 2015

Present: Jon Smith, John Adams and Sue Wagstaff

- Minutes of previous meetings

The minutes of the meeting on 10th March 2015 were approved and then signed by the Chairman

- Matters arising

Update on action points from previous meeting –

JS –

1. Not heard back from Nick Cahill but will chase and try and arrange meeting for early April

2. Document adopted and already being used in AONB. Kath Statham has offered to give training on application.

3. Awaiting response form Rob Lacey

4. Outstanding but will deal

5. Outstanding – will contact AONB for copy of their protocol

6. Awaiting response from Rob Lacey

At this point JA reported a recent news item about Teignbridge where planning applications were now considered at Parish level unless a specific request made. JS agreed to explore this further with Rob Lacey

JA –

- Has spoken to James Evans who intends stating that when the RNDP is adopted it will be legally binding whereas the SPD is for guidance only but he will point out the anomaly on height of turbines. He has not spoken to Dan Nicholls. It was agreed that JA would draft response from RNDP for approval and submission by JS to Cornwall Council

- Has spoken with both Brian Willis and Ralph German which has not produced any assistance on renewable energy so JA will produce document

- Has reviewed ‘A fair deal for rural communities’ report which he will circulate, but feels will be useful when trying to restrict second homes

SW – 1. Outstanding

- Review of SG meeting

All agreed it had been a good meeting with all attendees participating. In view of the lively discussion on the ‘Implementation’ Team it was agreed that the name was misleading and the minutes of the initial meeting should be published as an open MT meeting with guests from each parish. Also the purpose and activities sheet needed improvement – JA to deal.

- Review Project Plan activities and actions

Assessment of planning applications –

Following on from SG meeting – it was agreed JS should ask Julian German to chair parish cluster sessions but MT will provide training material. Also agreed should include all SG members and any other interested parties. JS has spoken to Geoff Pring who has offered to assist and will be meeting him after this meeting to discuss – agreed should ask if he is prepared to lead project and to discuss system needed. Possible other members of checking team were discussed. Initial thoughts are: Geoff and ‘team’ of volunteers to assess all applications against the Plan and report back to MT who then pass to Julian German and parish councils for final decision. Also, the overall system and performance of the Plan will need to be assessed by MT, Julian German and existing group of representatives from each parish.

Agreed needed to start ‘trial’, check this proposal with Julian German and seek approval of SG at their next meeting.

Affordable Housing – JS to contact secretary of St Just CLT to check progress

Conservation Area Management Plans –

Agreed need to get started – JA to contact Caroline Coldwell and ask her to collect her preferred volunteers and provide possible dates for first meeting, preferably before Easter. JS will speak to Jim Hetherington to assess when he will be available, and also contact Nick Cahill to obtain date for meeting.

Design Guide –

Agreed needed to find a project leader – possible candidates discussed.

JS suggested needed to check responses to consultation comments which referred to Roseland design guide – SW offered to provide list – and it was agreed to ask Alison Golding to check these against adopted Carrick Design Guide.

- AOB – None

Meeting closed at 12 noon				S Wagstaff

Action points –

JS –

- Chase Nick Cahill and try and arrange meeting for early April

- (Restated) Contact Jim Hetherington to establish suitable dates for initial team meeting

- (Restated) Contact AONB for copy of their protocol

- Discuss with Rob Lacey Teignbridge model of assessing planning applications at parish level

- Ask Julian German to chair parish cluster sessions

- Contact secretary of St Just CLT to check progress

JA –

- Draft response on renewable energy from RNDP for approval and submission by JS to Cornwall Council

- Circulate ‘A fair deal for rural communities’ report

- Improve ‘Implementation’ team purpose and activities sheet

- Contact Caroline Coldwell and ask her to collect her preferred volunteers and provide possible dates for first meeting, preferably before Easter.

SW –

- (Restated) Review Neighbourhood Planning and Community Buildings details to assess if any grants would be available for housing projects.

- List responses to consultation comments where referred to Roseland Design Guide