Minutes of Closed Meeting of Roseland Neighbourhood Development Plan (NDP) Management Team

at Little Treviles 10am on 1st May 2014

Present: Jon Smith, John Adams, Colin Hastings, Graham Webb and Sue Wagstaff

- Minutes of meeting 15th April 2014

Approved and signed

- Matters Arising

None

- LLCA

A review meeting had been held yesterday (30th April) at Scorrier with June Crossland (JC) and Kath Statham (KS) with Geoff Pring (GP) and Keith Fisher also attending. St Just and Philleigh parishes have completed and the remaining 3 should be done by 10th April when a closing LLCA meeting will be held at Ruan Reading Room. JC, KS and GP will then draft the final document. A consultation event is scheduled for Saturday 14th June in Portscatho to obtain the views of the public which will be added to the LLCA. It has been decided to combine this with a pre-consultation consultation on the draft NDP. The event to be advertised using usual media + A4 posters on Parish Notice boards + in the next letter.

- Village Character Assessment

June Crossland will be organising this but will not start until LLCA completed so will be too late for the draft Plan. She has however advised that a lot of information is already available in various places which may be sufficient and is to provide the relevant links, but this will obviously need someone to carry out research. JA asked GW if his Area Profile included sufficient information to produce a VCA. GW confirmed the Area Profile would be completed by 10th May and that it included Parish Character Assessments (PCA). GW offered to ‘beef up’ the content and on JS recommendation will ask David Hall for his assistance.

- Conservation Area Management Plan

JS explained that Julian German had instigated this and JS has spoken to Nick Cahill (NC) as suggested by Sarah Arden (SA). NC confirmed that his department does not have the resource to prepare a plan but will give time to explain how it should be done and act as consultants. NC also advised that the NDP could propose new conservation areas. JS reported that St Just Parish Council were keen to prepare a plan for St Mawes and Veryan PC had indicated a need for consideration of a conservation area in Portloe. This will be a Project after the Plan

- Design Guide

JA advised that he and CH have realised that preparation of a guide is more difficult than anticipated and to do the work justice should have been started much earlier. The options now are:

- No Design Guide, just basic policies in Plan

- As a) above + adopt Carrick Design Guide (CDG) in ‘Toto’ or in part but unsure if acceptable to the public.

- As a) + add design guide as project for 1 to 2 years’ time

JS reported that SA and Rob Lacey supported using the CDG and feel acceptable. JS pointed out will need to check what in the CDG is now out of date or irrelevant.

Julian German has indicated that he feels do not have sufficient evidence to produce a design guide and is concerned that if add as project to work on design guide as new annex document it will have cost issues. JG to speak to the planners.

GW indicated need to refer to both CDG and Cornwall Design Guide in NDP but there are only 3 relevant chapters in CDG and design principles do not change. Alternatively suggested could adopt CDG in full to preserve its principles and he confirmed the CDG was an adopted document

CH advised that he will be speaking to co-author of CDG tomorrow regarding any copyright issues and JS has been advised that the relevant person at CC will be back in the office on Tuesday 6th May (per SA)

JS suggested that the project to review effectiveness of the Plan will highlight whether need a Design Guide

JS asked CH if he had received any response from Philip Martin (PM) or Mark Datson (MD) regarding David Hubbard’s (DHu) draft design guide. No, so JA offered to contact PM and JS will contact MD

JA referred to the photos brought by both MD and PM which effectively started a photo library and asked GW if thought should widen this to include photos submitted by the public. GW suggested the photos could be used to illustrate the PCAs and it was agreed to include a request for submissions in the next letter.

CH asked GW if should produce a simplified document for the public but GW explained that there are a lot of explanatory documents ‘out there’ already

- Draft Policies/Draft Plan

JS stressed need to get draft plan out to all relevant parties so as to get feedback. JA suggested could have draft completed 80-90% by 15th May but was concerned those charged with the review would not consider the full implications. JS expressed view that enough ‘experts’ were involved who would study the document in depth.

GW referred to the diagram on page 10 of the draft as he felt a consultation stage had been missed and needed to ‘back fill’ options to show full process – JA agreed to complete.

GW also thought the order of subjects on page 20 of the draft should be explained to the SG i.e. not shown in order of importance per Q2

GW also voiced concern that both Economy and Renewable Energy could be difficult areas – suggested small mail shot to gather views. He felt there was no reference to tourism in the economy and suggested, and all agreed, that should gather views of Tim Light, Toby Ashworth and Rob Wing and GW offered to compose a question for JS to present to all 3.

GW had already drafted a possible policy on the economy as he felt the comments submitted highlighted tourism and small businesses.

CH offered to analyse qualitative data with focus on economy and tourism.

JA requested help/approval from those present on policies and then proceeded to go through each policy in detail:

Landscape:

LA1 OK, merge LA2 and LA4, merge LA3 and LA6, merge LA5 and LA7, merge LA10 and LA11 – all agreed.

Villages and hamlets:

Page 26 - Replace ‘Village’ with ‘Parish’ for Character Assessment

General principles:

GP1 - GW suggested should be first as delivers Vision

JA suggested could remove section if policies better accommodated elsewhere

GP6 – ‘Roseland’ changed to ‘adopted’ Design Guidelines

GP7 – going, but CH to write pre-amble regarding the process

GP8 – too prescriptive and GW feels more relevant to extensions

Housing:

GW suggested moving some pre-amble next to the policies

GW explained use of term ‘adequate parking’ and final paragraph of HO6

Commercial:

GW to write CD4 and JS to speak to Marshall Plummer of CC re: agricultural buildings and planning permission

Carbon Reduction:

Renewable Energy policies to be referred to Dan Nicholls (DN) of CC

CR1 to be amended to make applicable to all developments – new and extensions

JA with GW assistance to complete revisions by 12th May

GW suggested use Paul Mace for initial vetting

NOTE: CH left meeting at 1pm

GW enquired why his original draft policies for car parking and transport had been omitted. It was agreed to add back the policy on car parking for consideration and GW to re-submit policy on transport with especial reference to ferry terminals and the like

- Action Plan for May 2014

MT meeting on 12th May 10am Little Treviles to finally check Plan and then JA will send to print. Should be back on 15th May ready for distribution by hand/post/email to Parish Clerks and SG members

SG meeting 21st May will be taken up completely with the Plan review and to approve slight change made to the Vision statement

Letter to go out in May – 4 sides with poster for event on 14th June, a letter from JS and 2 diagrams from pages 18 and 19 of draft Plan

Meeting end of May with Planning Aid etc.

- AOB

None

Meeting closed at 1.30pm				S Wagstaff

Action points:

GW –

- ‘Beef up’ the content of Parish Character Assessment with assistance of David Hall

- Compose a question regarding tourism and economy for JS to present to Tim Light, Toby Ashworth and Rob Wing.

- Write Commercial development policy CD4

- Re-submit policy on transport with especial reference to ferry terminals and the like

JA –

- Contact Philip Martin for review of DHu draft Design Guide

- ‘Back fill’ options to show full process

- With GW assistance complete revisions by 12th May

JS –

- Contact Mark Datson for review of DHu draft Design Guide

- Present question on tourism and economy to Tim Light, Toby Ashworth and Rob Wing.

- Speak to Marshall Plummer of CC re agricultural buildings and planning permission

CH –

- Analyse qualitative data with focus on economy and tourism

- Under General Principles - write pre-amble regarding the planning process to replace GP7