Minutes of Closed Meeting of Roseland Neighbourhood Development Plan (NDP) Management Team

at Little Treviles 9.00am on 2nd October 2014

Present: Jon Smith, John Adams, Colin Hastings and Sue Wagstaff

- Minutes

The minutes of the meeting held on 29th September 2014 were approved and signed by the Chairman

- Matters arising

None

- Assessment of responses to Consultation

JA has transposed comments and responses/actions onto a spreadsheet in a document which will eventually be posted on the website. He has also started a list of the changes made to the Plan document, and started noting the changes on version 20 which will all appear in red.

Having all individually reviewed the spreadsheet it was agreed that they would work through discussing any areas causing concerns. JA recorded the changes/decisions.

CH noted that although some answers were consistent, others needed standardising and specifically mentioned those relating to policy HO8, defined settlement boundaries, use of digital media and insertion of a reason where no change made.

All agreed to remove the names of individuals at Cornwall Council from the document.

JA advised that following referral back to the Transportation Service of Cornwall Council it has been made clear that their reference to ‘travel plans’ only relates to large developments of over 250 units.

‘Major developments’ were discussed again and it was agreed that the MT needed to review how to use the Tamar Valley AONB Management Plan. All agreed with JA’s suggestion that a definition of major developments could be given in another Important Note at the start of the policy section.

It was agreed to seek clarification from Cornwall Council as to whether the existing Plan policies for commercial development will cover phone masts and military and government establishments.

Andrew O’Brien of the Affordable Housing department of Cornwall Council had recently submitted a response to the consultation but although outside the period it was agreed that the content should be discussed at the forthcoming meeting with Rob Lacey (RL) and Sarah Arden (SA).

SW was asked to write to another late response received this week.

JA agreed to complete updates to the consultation responses and Plan documents by Monday 6th October for JS to forward to RL, SA, June Crossland, the AONB and Jo Widdecombe at Planning Aid

- LLCA

JS had circulated copies of email correspondence from Caroline Coldwell and June Crossland and all were pleased that this was moving forward but asked JS to remind them that the document was needed by 29th October.

However from their discussions it has become apparent that it would not be possible to merge the Area Profile and LLCA work on settlement boundaries as one is factual and one is emotive.

- Hinterland

JS had already circulated to the MT Kath Statham’s (KS) guidance notes and had suggested to Geoff Pring (GP) that he meet KS to discuss the process before starting to produce the map. CH pointed out that GP will also need to document how he gets from the guidance notes to the final map.

- Cornwall AONB Unit

JS has spoken to Collette Beckham of Cornwall AONB and learnt that Cornwall Council are threatening to cut their funding of the unit as part of their budget reduction plans. The unit’s other source of funding – DEFRA – is also apparently under threat and the MT expressed concern over how the NPPF could be delivered and how the AONB Management Plan could be produced which is a legal requirement.

It was agreed that JS should write a letter of support and also ask Sarah Newton MP to contact DEFRA

- Cornwall Local Plan

JS advised that a large number of amendments have been made since the consultation (in which he participated) and he feels the document must be checked again and asked if he should do this. JA suggested that as Graham Webb will need to check for conformity he would be best placed for the task but all agreed it would be better to have more than one overview.

- Consultation Statement

CH has already sent his draft to the MT and explained that he would appreciate the other members reviewing his work. Also there were places marked where JS and/or JA needed to input sections. It was also agreed to seek Julian German’s input on the early stages of setting up the Plan.

- Basic Conditions Statement

JA has given Graham Webb’s document a brief look through and believes he has done a good job. However GW has already advised that he cannot complete the document until the submission Plan is finalised

- AOB

CH acknowledged he still had to produce a report on the summer events.

It was agreed to hold the November SG meeting on the usual third Wednesday of the month.

As it is 3 weeks until the next SG meeting JA suggested and all agreed that the SG members deserved an update on progress. JS suggested he prepare an interim Chairman’s report for circulation – this suggestion was adopted.

JA expressed the view that at the October SG meeting they needed to obtain SG approval/permission to go to the Parish Councils with the submission document

Meeting closed at 10.45am					S Wagstaff

Action points –

JS –

- Remind Caroline Coldwell and June Crossland that the LLCA document is needed by 29th October.

- Write a letter of support to AONB and also ask Sarah Newton MP to contact DEFRA

- Check amendments to Cornwall Local Plan and ask Graham Webb to do likewise

- Review Consultation Statement and input sections where indicated

- Prepare interim Chairman’s report for SG members

JA –

- Review Consultation Statement and input sections where indicated

CH –

- Produce report on summer events

SW –

- Write to sender of late response