Minutes of Closed Meeting of Roseland Neighbourhood Development Plan (NDP) Management Team

at Little Treviles 10am on 10th March 2014

Present: Jon Smith, John Adams and Sue Wagstaff

Apologies; Colin Hastings

- Design Guide

David Hubbard (DH) joined the meeting to present his work so far. It was agreed that Trudi van der Wolde should start typing up his draft and DH should continue with the guide and also list additional input required e.g. photos, maps, and sketches

It was accepted that the LLCA and village character assessment may produce suitable material and Philip Martin could assist with examples

DH asked that Mark Datson look over his work, completion/review of which is scheduled for 31st March

JA commented that some of Graham Webb’s Area Profile and also the mapping exercise may ‘dovetail’ with the Design Guide and it was suggested that a joint meeting should be held to see how all parts fit into the overall Plan

- LLCA

JS reported training on Sat 29th March went very well and Keith Fisher has already organised their first ‘outing’.

June and Kath want follow up meeting at Ruan Sat 29th March so volunteers can share experiences

JA is chasing for attendees for second session on 17th March which June Crossland is running. Also Geoff Pring to attend, who has completed his ‘mapping’

Expect exercise to be completed in 4-6 weeks

After LLCA completed village character assessment will be carried out but date not yet set

Also June and Kath have suggested that when all processes/work done a public consultation event should be held

- Roseland Magazine

JA has drafted article for April magazine – content agreed

- Results letter

JS has first draft – accepted. JA to investigate most cost effective way to print letter and Q2 results.

- Q2 update

In absence of response from Terry Hedge JA agreed to complete corrections. JA will also check Parish responses to questions 13, 16 and 19 and double check all results by 17th March.

Agreed public release to use same basis as Parish councils. Will be emailed to SG for agreement (with letter)

JA confirmed his analysis of final tranche of comments should be completed soon

JA has spoken to Frances Wall regarding renewable energy. JS agreed to speak to Julian German to discover if there is any one with Cornwall Council who could assist

SW agreed to start splitting comments by Parish

SW has spoken with Emma Ball who has requested 40 random forms to complete audit of quantitative data

- Preparation for meeting 11th March – Planning Aid

JS and JA to attend. Will take Q2 results to discuss how to proceed. Also raise issue of AONB/National Parks

- Preparation for meeting 14th March – Planners

Meeting requested by Sarah Arden and Rob Lacey and although RL will be absent he is preparing paper for meeting

It was agreed to mention problem of definition of ‘local’

JA to list options from Q2 comments

- Preparation for meetings 17th March – MT and LLCA

As LLCA training requires Ruan for day agreed move MT to Veryan S&S Club

LLCA – Agreed need to hold second training session but hope will be more than 2 participants

MT – GW will be reporting on Area Profile and mapping exercise

- Preparation for meeting 19th March – AONB and SG

AONB – JS has obtained 2 copies of their Delivery Plan but not sure how powerful it is. Agreed AONB is good ‘headline/banner’ but need to write policies in NDP.

JS and CH to attend

SG – Run through recent meetings held and outcomes (and conflicts where exist)

It was agreed that JS would approach GW to ask if he would produce Planning Context for Plan

JA to explain ‘new’ Activity List and content, and also the evolving shape of the Plan

Meeting closed at 12.30pm				S Wagstaff