Minutes of Closed Meeting of Roseland Neighbourhood Development Plan (NDP) Management Team

at Gerrans Memorial Hall at 11.40am on 10th July 2015

Present: Jon Smith, John Adams and Sue Wagstaff

- Minutes

The minutes of the meetings on 22nd June were approved and signed by JS

- Matters arising

Action points from the previous meeting reviewed –

JS –

- Meeting arranged with Sarah Newton MP for Friday 17th July

2, 3 and 4 Done

5 – 8 Outstanding and to be carried forward

JA –

- Partially completed

2 and 3 Done

SW - Done

- Referendum

JS had forwarded an email received from John Simmons of Cornwall Council prior to the meeting. The content of the email and the documentation attached were discussed. It was agreed that JS would enquire whether the wording of the question for the referendum could be changed slightly to use more familiar terminology. When the wording of the Notice of Referendum has been finalised it was agreed that some copies should be laminated and displayed throughout all parishes. As regards observers of the ballot and count it was agreed that there was no need at the ballot but that the Steering Group and the extended project team should be invited to attend the count on Friday 21st August (JS to check there will be room for all to attend)

Due to the referendum falling the day after the scheduled date for the August SG meeting it was agreed to move the meeting to early the following week.

- Publicity

JA had circulated a draft of the article for the August Roseland Magazine which was approved. This will also be circulated via Roseland Online (with a calendar entry as well – SW to arrange), by email (JA) and via Facebook (Colin Hastings)

JA is to complete the draft of the pre-referendum letter/summary/poster and circulate to the MT for comment. It was agreed that the distributors must be made aware of the importance of completing delivery during the first 2 weeks of August. JA is also working with David Spreadborough on the flyer for the Roseland Magazine. An early draft was discussed together with timescales for approval, printing and delivery to the magazine and it was agreed that volunteers for contact points in each parish for those needing assistance getting to vote were needed prior to the SG meeting – SW agreed to send an email request and collect names and also to check the latest date for acceptance of the flyers by the magazine.

Attendance at local events with a stand/displays was discussed and it was agreed to be unnecessary in view of the other forms of publicity being utilised. (SW to respond accordingly to an enquiry from St Mawes Carnival organisers)

It was agreed that Hub Radio should be used during the 2 weeks just prior to the referendum but the format has yet to be agreed.

- SG Meeting 15th July

James Evans of Cornwall AONB will be attending and giving a presentation at the start of the evening. JS will prepare the agenda and his report. It was agreed that a copy of the article for the August edition of the Roseland Magazine should be circulated with the material for the meeting as it includes information about the referendum. It was also agreed that availability of distributors for the pre-referendum letter should be checked and the need for prompt delivery stressed.

- Meeting with Rob Lacey

It was agreed that before the meeting is arranged a list of subjects that need to be discussed must be agreed. Matters mentioned included:

Clarification on permitted development rights, both agricultural and for extensions

Discussion regarding CAMP policies

Situation regarding Roseland Design Guide now no longer mentioned within Plan document

After referendum what documents need to be retained or are they then the property of Cornwall Council?

JS agreed to draw up an initial list of subjects and then circulate to the MT to add/comment

- St Just planning committee meeting

Following the PAG assessment of the planning application for Venton Gassic in the St Just parish JS has been invited to attend the next meeting of their planning committee on Monday 13th July. He will take the opportunity to explain the role of the PAG and will encourage parish councillors to join as assessors.

- Conservation Areas

JS explained that Caroline Coldwell although invited had been unable to attend the meeting today to give an update on the CAMP project and it was agreed that she should be invited to attend next Friday, 17th July

- AOB

Following on from point 8 above JA suggested (and all agreed) that going forward every 4 weeks the Friday meeting should be set aside for reviews of all the projects with the project coordinators given 3/4 hour slots to provide a report on progress.

The affordable housing project was discussed – it was agreed that JS will arrange a meeting with the Cornwall CLT and also a meeting with Nick Marsden and Rob Lacey to set the ‘background’. After this it was agreed that a coordinator must be sought.

JA suggested and all agreed that to progress matters highlighted in the Plan but not contained in policies advisory articles could be submitted to the Roseland Magazine e.g. Information on more visually acceptable solar tiles – suppliers, costs etc.; information on owl boxes – suppliers and cost.

Meeting closed at 12.50pm					S Wagstaff

Action points –

JS –

- (Restated) Chase up response on permitted development notifications

- (Restated) Set up meeting with Nigel Doyle and Rob Lacey to discuss the planning process

- (Restated) Set up meeting with Rob Lacey to discuss the implications of the examiner’s instructions to remove all reference to a Roseland Design Guide from the Plan document

- (Restated) Set up meeting with Nick Marsden to try and establish the ‘true’ figures for housing requirements

- Enquire whether the wording of the question for the referendum could be changed slightly to use more familiar terminology.

- Check there will be room for all to attend the referendum count

- Draw up an initial list of subjects for meeting with Rob Lacey and circulate to MT

- Arrange a meeting with the Cornwall CLT

JA –

- Complete letter/summary/poster for referendum

- Complete flyer for Roseland Magazine

SW –

- Create Roseland Online calendar entry for referendum

- Send an email request to SG for coordinator/drivers to transport voters to polling station

- Check the latest date for acceptance of the flyers by the magazine.