Minutes of Closed Meeting of Roseland Neighbourhood Development Plan (NDP) Management Team

at Little Treviles 10am on 23rd May 2014

Present: Jon Smith, John Adams, Colin Hastings and Sue Wagstaff

Meeting called to discuss the way forward and JA expressed concerns about keeping to present timescales.

Steering Group

All agreed that the SG meeting on 21st May highlighted the difference in knowledge between the MT and the SG regarding the principle of a Neighbourhood Plan. Obviously the SG has not had the benefit of the ‘journey’ the MT has taken and the depth of knowledge they have had to acquire in a short space of time. It was agreed that the forthcoming workshop should focus on raising the awareness of the SG and ensuring that they understand the process and have sufficient information to be able to vote on the draft Plan at the June SG meeting. JS proposed that this vote should be by secret ballot.

JA highlighted the pages of the draft Plan he felt they should focus on at the workshop, being pages 14 to 18 inclusive. The content of pages 14 to 16 inclusive have already been agreed by the SG so page 18 may need further explanation. JA agreed to produce a document showing the link between the 5 Objectives and the various Policies. It was also agreed to use poster size prints of these pages as part of the display at the 14th June event.

CH suggested need to explain to the SG that the MT have obtained expert help with the wording of the Policies but the SG need to support the underlying strategy.

If sufficient members of the SG raise issues which are outside the draft Plan it was agreed that these should be added to the Project list for future consideration/evaluation and a flip chart used at the workshop to record any raised.

All agreed that JA was the best person to lead the workshop which was set for Tuesday 10th June at either St Mawes Millennium Rooms or Ruan Reading Room with 6.30pm start.

As some members of the SG had expressed a wish to see the experts’ comments on the draft JA agreed to scan the relevant pages. He will then when advising details of the workshop offer to email the comments to those who request them.

Cornwall Council

JA expressed concern that their answers to queries may not be available in time.

JS gave updates:

- Dan Nicholls (DN) re Renewable Energy – meeting scheduled for week beginning 16th June but should have DN’s comments on RE policies prior to that

- AONB – meeting arranged for Wednesday 11th June in Truro with June Crossland (JC) and Collette Holden. JA to email updated draft of Plan prior to meeting so they can give AONB view. JC had indicated that although the existing AONB Plan expires in 2-3 years the strategy will remain unchanged but they depend on NDP’s to provide the detail and evidence base

- Not yet been able to speak to Nick Marsden re Affordable Housing

- Awaiting response from Rob Lacey (RL). CH expressed concern over when RL could provide feedback. All agreed that he was the best person for the job and they should await his response.

Draft Plan update

JA said he was happy to update the draft referring to all the comment/input received so far. It was agreed that he should obtain Angela Warwick’s input on the wording of both the Policies and the pre-amble.

Following comments made at the recent SG meeting it was agreed that mention should be made in the introductory section of the changing face of farming and its impact on the Roseland.

JA also wants to incorporate an explanation that all the Policies should be considered together and not as individual Policies in isolation.

JA agreed that Version 17 should be with the MT by Friday 30th May

JA explained that the Plan would be a paper document but the 3 annexes would be on the website, namely the Area Profile, the maps and the LLCA

It was agreed that Graham Webb (GW) should be asked to complete the Area Profile by 6th June to allow time for JA to ‘tweak’ the look/style to conform to the Plan.

Deadline for completion of maps from GW to be 6th June and JS offered to check if CC have facility to scan large documents

JA asked and CH agreed to resurrect and complete his list of possible future projects drawn from community feedback.

Evidence Base – JA explained that some detail will be included in the Plan document but the bulk of it will either be on the website or stored on computer/memory stick

References – it was agreed that only the more obscure should be shown in the document and JA will incorporate during the second half of June

Relevant Higher Level Policies – JA asked and CH agreed to produce a table showing the relevant paragraph number/name of each Higher Policy relevant to each of the Plan Policies. This will form part of the Evidence Base and some detail will be incorporated in the Plan document.

Next meeting Monday 2nd June at Little Treviles to consider Version 17 of draft Plan and Project List

Meeting closed 11.25am						S Wagstaff

Action Points:

JA –

- Produce document showing link between Objectives and Policies for workshop

- Scan experts’ comments ready to email

- Produce Version 17 by 30th May

CH –

- Resurrect and complete Project List for meeting 2nd June

- Produce table of Relevant Higher Level Policies

JS –

- Check if CC can scan maps

SW –

- Book venue for workshop – 1st choice = Millennium Rooms, 2nd = Ruan Reading Room