Minutes of Closed Meeting of Roseland Neighbourhood Development Plan (NDP) Management Team

at Little Treviles, 9.30 am on 26th February 2014

Present: J Smith, John Adams, Colin Hastings + Sue Wagstaff

- MT meetings: Open/Closed

JS proposed that all MT meetings be minuted to be seen as open and honest - unanimous agreement.

Difference between Open and Closed to be explained at next Open meeting 3rd March 2014

- Q2 Final figures

JA advised about half way through audit of Q2 quantitative data and explained how/why amending figures. Anomaly over number of completed forms to be solved and Terry Hedge to correct/amend results

JA to record how calculated so clear how reached results

JS approved as need to avoid any dispute if possible

- Parish Councils

JS reported very positive response from recent Ruan parish meeting and is to attend meetings at St Just 3rd March and Gerrans 4th March. Has decided will not use PowerPoint presentation to explain results as prefers paper option – JA to use Q2 as basis and show results as numbers and percentages against each question. Also add slides selected by JS on front and back pages

Agreed that after Plan completed JS will address Parish Councils about retaining Steering Group to assist in implementation/successor objective

- Q2 Final figures mail out

JA suggested use Tattenhall example as basis – about 4 pages and very factual – JS & CH agreed. JA said could be ready by 10th March. Distributed by hand and electronically

If deemed necessary, hold public presentations, one per parish

- Stakeholders

JS reported about 100 letters sent but minimal response. JA has 4-5 responses

JS has meeting arranged with Toby Ashworth of Nare Hotel where he will present figures

- Feedback from Sarah Arden (SA)

JS talked through email dated 25th February from SA which was discussed and all agreed was helpful

CH feels NDP weak on marine side (with reference to AONB) JS advised that background information to AONB policies will be available to NDP

JS stressed needed to keep close to time frame to complete (Note: NDP can be amended/changed in future if required BUT have to go through whole process again) Feels LCA and CC all coordinating. Suggested arrange meeting/’summit’ with all parties involved

JA feels need advice on objectives, and policy writing forum needed – JS advised that Jo Widdecombe and Angela Warwick have offered a meeting, just need to agree a date

JS suggested another meeting with SA and Rob Lacey and possibly RE expert Dan – agreed by JA and CH – JS to arrange

10.30am David Hubbard (DH) joined meeting

DH attended to discuss design guides – he explained his role with regard to St Just Parish Council and planning applications, and brought examples of existing design guides – the favoured one (by him and the NDP advisors) being the Carrick Guide which is referred to in the Cornwall Design Guide

It was agreed that a Roseland specific design guide is expected according to Q2 covering residential, commercial and agricultural aspects and it was agreed that as well as written advice there should be relevant photos – some will be produced from the LLCA but CH suggested could be passed back to residents via email request for photo examples of good and bad design

Following much discussion about content DH agreed to produce a template indicating headings and format within 7-10 days for consideration by MT before proceeding further

When DH has completed content JA offered to formulate the document and it was suggested Trudi van der Wolde could assist

Discussion then turned to implementation/compliance – JS suggested need exhibitions in each parish, and ‘legacy’ group to assist parish councils in screening process

DH then left the meeting

11.30am Alison Golding (AG) joined meeting

AG talked through her ‘paper’ - Roseland Plan: The full time residence issue. Much discussion followed regarding what is possible to include in the NDP from a legal perspective. CH suggested refer to other areas’ NDP and their progress with the second homes issue (e.g. Sothern Lakes)

JS to pass AG’s Annex 1 to SA for comment and then back to AG. If favourable response, send Annex 2 as well

All thanked AG for her thorough and prompt response

AG left the meeting

JA suggested should use AG as a ‘sounding board’ when drafting the Plan to ensure don’t create problems

- Draft Plan template/Graham Webb (GW)

JA has done no more to template/GW is still writing the Area Profile – await what he produces

- LLCA/2nd workshop

JS reported all in place for first training session 8th March – JA confirmed 17 attendees and he will attend with JS. 10 left to attend 2nd session – 2 possible dates - 17th or 19th March – it was agreed to contact 10 and ask them for preference and then go with most popular date

- AOB

- Agenda for Open MT 10am 3rd March in Ruan – 1) Q2 progress 2) Project plan and progress review 3) Minutes.

Subsequent MT meetings – Closed 10th March and Open 17th March both at Ruan

SG meeting 19th March at Memorial Hall St Mawes

- CH has picked up some names from Q2 where comments indicate particular knowledge of design and renewable energy – suggests involve in future consultations

- JA to follow up Frances Wall who is looking at issue of Renewable Energy

- CH meeting Dan and Gavin Black Saturday 1st March - it was agreed he should assess what they can offer – Dan is sustainable appraisal expert and Gavin is from Natural England in Exeter – marine in South West

- JA voiced thoughts on carbon reduction and the NDP – JS suggested could fall under legacy organisation to assist parishes in encouraging carbon reduction – CH indicated should keep note of scope of legacy organisation

- CH concerned about AONB and NDP – JS indicated June Crossland understands and we should enlist their help. CH will research other organisations he feels relevant to NDP

Meeting closed 1.05pm                                 S Wagstaff 27/02/14