Minutes of Meeting of Roseland Neighbourhood Development Plan (NDP) Steering Group

at Veryan Sports and Social Club, 7 pm on 20th November

- Present				Parish / Other	Steering Group Member?

John Adams		JA	Ruan Lanihorne			Y

Mr Fender			Veryan					N

Mrs Fender			Veryan					N

Keith Fisher		KF						N

David Giles		DG	Ruan Lanihorne			Y

David Hall			DHa	Ruan Lanihorne			Y

Colin Hastings		CH	Gerrans				Y

David Hubbard		DHu	St Just 					Y

Julie Johns			JJ	Veryan					Y

Derek Julyan		DJ	Philleigh				Y

Jon Smith			JS	Veryan					Y

David Spreadborough	DS	Philleigh				Y

Sue Wagstaff		SW						N

Graham Webb		GW	Veryan					Y

Christine Williams	CW	St Just					Y

Brian Willis		BW	St Just					Y

Rob Wing			RW	Philleigh				Y

Apologies: Julian German, Ralph German

- Declarations of Interest

None

- Public Participation

None

- Minutes of the Meeting on 16th October 2013

The minutes were accepted as a correct record (D Hall proposed; D Giles seconded).

- Matters Arising

DHa circulated a folder of material to members of the SG concerning levels of protection of natural habitats in the NPPF. He said that the ‘best practice approach is to avoid locating developments on designated sites (statutory, non-statutory or semi-natural habitats). He reported that the Cornwall Wildlife Trust has agreed to send a representative (Cheryl Marriott) to our December SG meeting to give us more information and to answer questions.

CW commented (and others supported the idea) that AONB and SSSI (etc) legislation should be incorporated into/associated with the NDP to strengthen protection of the Roseland.

- Chair’s Report

This is appended.

Update on item 8. JS has arranged a meeting of the MT with our consultants on 26th November. At this meeting, a date will be agreed for a second meeting of the consultants with the SG.

JS explained the timetable of meetings in the next 2 months.

- SG Meeting on Wednesday 20th Nov	Normal Monthly Meeting

- MT Meeting on Tuesday 26th Nov	Meeting with Consultants

- MT Meeting on 2nd December		Review progress on Q2 and other actions

Prepare material for Special Steering Group Meeting

This includes an draft updated Project Plan

- Special SG Meeting on 4th December	Discussion about forward Project Plan

- MT Meeting on 9th December		Prepare for next Steering Group Meeting.

- SG Meeting on 18th December		Normal Monthly Meeting

Includes presentation from Cornwall Wildlife Trust

- MT Meeting on 6th January		Review progress on Q2, Draft Project Plan etc

Prepare material for next Steering Group Meeting

- SG Meeting on 15th January		Normal Monthly Meeting

The Chair’s Report was accepted unanimously (Proposed by DG, seconded by BW).

JS explained about the problems with the email voting on Q2. He said that JA is writing a summary report to explain the process going from distribution of Q1 to the finalising of Q2.

- Q2 – Progress Report

JA summarised that Q2 has been printed and recorded numbers given to Parish representatives. Distribution has been completed in some Parishes but not in others. There are some issues with (for example) houses with people who are residents but they are not on the electoral roll.

SW reported that 109 had come back so far. Good returns from St Mawes and Veryan.

CH talked about the Drop In sessions. Event dates are being publicised electronically and through posters (handed out at the meeting).

The main objective over the next 2 or 3 weeks is to get as many Questionnaires filled in and returned as possible. Colin asked SG members to try to help (especially) housebound folk. He also thought that anything that could be done to bring younger people on board would be good. RW thought it was a pity that we hadn’t been able to make the document available electronically.

JJ asked that spares should be available at Drop in Events. JA will give spares to CH for the events.

GW suggested (and it was agreed) that we ‘catch’ more questionnaires in the first half of January by putting up posters, circulate emails and putting text in the January Roseland Magazine etc emphasising that it isn’t too late to ‘Have Your Say’.

- Project Plan Update

JA explained the process we’ll be going through in next 2-3 weeks to generate detailed activities for the period till the Draft Plan has been produced.

It was understood that the amount of work will be large but it was clear that material produced previously (eg Carrick) or for related areas (Landscape Character Assessments, Design Guide) may be useable (with suitable modification) and thus will save us much work.

- Activity List

JA circulated the latest version. It was agreed that (updates of) the document should be put on the website.

- Finance

JS circulated his financial summary (Appended). BW gave us an update on the situation re: issuing cheques. The new account was opened on 28th October. Nonetheless the chequebook has not yet arrived (despite multiple reminders). Cheques are being written out of the ‘old account’ which will have to be reimbursed.

3 invoices were presented for payment this month. DG/DHu proposed and seconded approval for payment. This was approved unanimously.

JS reported that the Council have said we will have to pay for maps.

JS proposed that the MT is allowed to sanction payments of up to £100 per item without prior authorisation by the Steering Group. GW suggested that this should be capped at £1000 per month. The proposal was seconded by DJ and approved unanimously.

- AOB

GW asked about the meeting with the consultants and whether it was restricted to the MT. JS said yes but that we would try to set up the SG meeting with the consultants asap.

DG asked whether SG members will be available for the various Drop In meetings. CH has asked for information from Parish Reps and will be coordinating this.

MEETING CLOSED AT 20.25.

FINANCE REPORT FOR ROSELAND NDP STEERING GROUP MEETING TO BE HELD ON 20 NOVEMBER 2013

RECEIPTS AND EXPENDITURE AS AT 18 NOVEMBER 2013

| DETAILS | RECEIPTS | EXPENDITURE |
| --- | --- | --- |
| Grant from Cornwall Councillor | £1,000.00 |  |
| Community Development Foundation Funding £7,000 agreed with an initial advance of £6,300 | £6,300.00 |  |
| Printing Budget £4,440 |  | £408.98 |
| Website Costs Budget £580 |  | £226.38 |
| Stationery Costs £300 |  | £43.20 |
| Events and Meeting Costs £1,480 |  | £186.00 |
| Banner and Display Board Costs £200 |  | £198.60 |
| Total | £7,300.00 | £1063.16 |
| Balance | £6,236.84 |  |

INVOICES FOR PAYMENT:

- JOHN ADAMS  Printing of “Questionnaire 2” £1,375.20

- JON SMITH  Purchase of boxes for “Questionnaire 2” and Laminating Pouches £38.75

- GERRANS MEMORIAL HALL Hire of Meeting room £24.00

The Monitoring Report has been submitted to the Community Development Foundation for our Grant. A request has also been submitted to allow us to use some of the grant money for the purchase of maps and has been accepted.

I would like to make a proposal that the Management Team be allowed to sanction expenditure up to £100 per item without prior endorsement from the Steering Group.

Jon Smith, Chairman, 18 November 2013